AI Co-op Internship Training Plan

Predictive Maintenance Track | 7-Week Program | Power BI Included

Program Duration: 7 Weeks | Students: 2 | Major: Artificial Intelligence | Environment: Google Colab + Power BI

This package expands the previous plan into a 7-week training program. Week 6 is dedicated to Evaluation and Optimization, and Week 7 is reserved for the Final AI Maintenance Advisor Demo. This gives students enough time to validate and improve the model before presenting the final solution.

1. Program Summary

This program is designed for university Co-op students majoring in Artificial Intelligence. The training objective is learning through a practical Predictive Maintenance project using synthetic, non-sensitive training data. The structure uses Google Colab for Python, data analytics, and Machine Learning, and Power BI for dashboarding and business insight communication.

The project uses synthetic training data only and does not require any real company data.

Power BI is included as a clear business dashboard deliverable, while the ML model remains in Google Colab.

Week 6 focuses on evaluating, optimizing, and explaining the model before students build the final demo in Week 7.

2. Required Tools

| Tool | Type / Purpose | How It Will Be Used |
| --- | --- | --- |
| Google Colab | Website / browser-based environment | Main workspace to write and run Python notebooks |
| ChatGPT / Copilot | AI assistant | Help students understand maintenance scenarios, write prompts, troubleshoot code, and summarize results |
| Python | Programming language | Basic scripting, data handling, and model development |
| Pandas | Python library | Read Excel files, clean tables, filter data, and analyze records |
| Matplotlib | Python library | Create basic charts in Colab |
| Scikit-learn | Python library | Build and evaluate Machine Learning models such as Decision Tree and Random Forest |
| Power BI Desktop | Business intelligence tool | Build a simple dashboard for failure trends, risk levels, and equipment insights |
| NumPy | Python library | Used indirectly for numerical calculations; no need to teach it deeply at the beginning |
| Seaborn | Python library | Optional library for nicer charts; not mandatory |
| Streamlit | Python library | Optional stretch tool; Colab demo is enough for the required final deliverable |
| PowerPoint | Presentation software | Prepare the final short presentation |

3. Training Data

The attached dataset is a synthetic Predictive Maintenance dataset. It includes equipment-related fields such as Equipment ID, Equipment Type, Air Temperature, Process Temperature, Rotational Speed, Torque, Tool Wear, Vibration, Pressure, Machine Failure, Failure Type, Risk Level, and Maintenance Recommendation.

Students will use the Training_Dataset sheet as the main dataset for Colab analysis and Power BI dashboarding.

The Data_Dictionary sheet explains each column.

The PowerBI_Dashboard_Guide sheet explains the dashboard pages and visuals.

The Evaluation_Rubric sheet provides the updated 7-week assessment criteria.

4. 7-Week Program Structure

| Week | Focus | Goal | Deliverable |
| --- | --- | --- | --- |
| Week 1 | Predictive Maintenance Foundations and Maintenance Intelligence | Understand Predictive Maintenance, equipment failures, sensor data, and AI-supported maintenance decisions. | Dataset understanding report, 3 failure scenarios, 10-prompt maintenance library, and mini Maintenance Advisor concept. |
| Week 2 | Python Fundamentals in Google Colab | Learn basic Python needed for the project. | Python practice notebook. |
| Week 3 | Data Analytics with Python | Read, clean, and explore the Predictive Maintenance dataset. | EDA notebook and data understanding summary. |
| Week 4 | Visualization, Power BI Dashboard, and Business Insights | Create Python charts and a basic Power BI dashboard to communicate maintenance insights. | Visualization notebook, Power BI dashboard, and 5 to 10 business insights. |
| Week 5 | Machine Learning for Failure Prediction | Train simple models to predict machine failure. | Decision Tree baseline, Random Forest model, and initial evaluation summary. |
| Week 6 | Evaluation and Optimization | Evaluate model performance, analyze errors, improve features/model settings, and finalize recommendation logic. | Model evaluation report, before/after comparison, improved model results, and final recommendation logic. |
| Week 7 | Final AI Maintenance Advisor Demo | Combine the Colab ML model, Power BI dashboard, recommendation logic, and final presentation. | Final Colab demo, Power BI dashboard screenshots, live demo, and 5 to 7 slide presentation. |

5. Detailed Weekly Plan

Week 1: Predictive Maintenance Foundations and Maintenance Intelligence

Day 1: Introduction to Predictive Maintenance and why industries use it.

Day 2: Understand key equipment and sensor data such as temperature, pressure, torque, vibration, tool wear, failure status, and risk level.

Day 3: Failure Investigation Workshop using sample equipment readings and ChatGPT/Copilot.

Day 4: Create maintenance-focused prompts to analyze sensor readings, failure risks, and recommendations.

Day 5: Present dataset understanding, 5 key variables, 3 failure scenarios, and 10 maintenance prompts.

Deliverable: Dataset understanding report, equipment failure scenarios, and maintenance prompt library.

Week 2: Python Fundamentals in Google Colab

Day 1: Learn Colab cells, running code, adding notes, and uploading files.

Day 2: Practice Python variables, numbers, strings, and print statements.

Day 3: Practice lists, dictionaries, and simple equipment reading examples.

Day 4: Practice loops and functions using simple risk threshold examples.

Day 5: Complete a Python practice notebook and explain each code block.

Deliverable: Python basics notebook with simple maintenance data exercises.

Week 3: Data Analytics with Python

Day 1: Read the Excel dataset using Pandas and inspect the first rows.

Day 2: Check data types, missing values, duplicates, and basic statistics.

Day 3: Explore Machine_Failure, Failure_Type, Risk_Level, Vibration, Torque, and Tool_Wear_Min.

Day 4: Group and filter the data to understand failure patterns across equipment types.

Day 5: Prepare a clean EDA notebook and summarize what each dataset field means.

Deliverable: EDA notebook and data understanding summary.

Week 4: Visualization, Power BI Dashboard, and Business Insights

Day 1: Create basic charts in Colab using Matplotlib to understand failure distribution and key variables.

Day 2: Open the Excel dataset in Power BI Desktop and load the Training_Dataset table.

Day 3: Build a simple Power BI dashboard with failure count, risk level distribution, failure type breakdown, and equipment type trends.

Day 4: Write 5 to 10 business insights based on both Colab charts and Power BI visuals.

Day 5: Present the Power BI dashboard and explain the most important maintenance insights.

Deliverable: Visualization notebook, Power BI dashboard, and 5 to 10 business insights.

Week 5: Machine Learning for Failure Prediction

Day 1: Define features and target variable. Use Machine_Failure as the main prediction target.

Day 2: Prepare the data for modeling, including categorical encoding and train/test split.

Day 3: Train a Decision Tree model as a simple baseline.

Day 4: Train a Random Forest model and compare it with the baseline model.

Day 5: Evaluate the first model version using Accuracy, Precision, Recall, and Confusion Matrix.

Deliverable: Decision Tree baseline, Random Forest model, and initial evaluation summary.

Week 6: Evaluation and Optimization

Day 1: Review model results and explain what Accuracy, Precision, Recall, and Confusion Matrix mean in the maintenance context.

Day 2: Analyze false positives and false negatives, and discuss which type of error is more critical for maintenance decisions.

Day 3: Improve the feature set by testing different input variables and checking their impact on the model results.

Day 4: Tune simple Random Forest settings and compare before/after results.

Day 5: Finalize recommendation logic and create a short Model Evaluation and Optimization report.

Deliverable: Model evaluation report, before/after comparison, improved model results, and final recommendation logic.

Week 7: Final AI Maintenance Advisor Demo

Day 1: Finalize the Colab demo input section for equipment readings.

Day 2: Connect the optimized model to the demo and show prediction, probability, risk level, and recommendation.

Day 3: Finalize the Power BI dashboard and capture screenshots for the presentation.

Day 4: Prepare the final presentation with problem statement, dataset overview, insights, ML model, optimization, dashboard, and demo results.

Day 5: Deliver the final live demo and project learning summary.

Deliverable: Final Colab demo, Power BI dashboard screenshots, final live demo, and 5 to 7 slide presentation.

6. Power BI Dashboard Requirements

Create one simple Power BI report using the Training_Dataset table.

Page 1: Maintenance Overview with total records, failure count, and risk level distribution.

Page 2: Failure Analysis with failure type breakdown and failure rate by equipment type.

Page 3: Sensor Insights with charts for vibration, torque, tool wear, and temperature trends.

Keep the dashboard simple. The goal is to communicate insights, not to build a complex BI solution.

7. Evaluation and Optimization Requirements

Compare at least two models or two versions of the same model.

Explain the Confusion Matrix in maintenance language.

Discuss false positives and false negatives from a business perspective.

Show before/after model scores after feature or parameter changes.

Finalize recommendation logic based on risk level and predicted failure probability.

8. Week 1 Maintenance Prompt Library Examples

Analyze the following equipment readings and identify possible maintenance risks.

Explain which sensor reading is most likely contributing to the failure risk.

Generate a maintenance recommendation based on temperature, vibration, torque, and tool wear.

Summarize the equipment condition for a maintenance supervisor.

Classify the equipment condition as Low, Medium, or High risk and explain why.

Identify which readings are abnormal and what inspection action should be considered.

Compare two equipment cases and explain which one requires earlier maintenance attention.

Explain how tool wear can increase the probability of machine failure.

Create a short maintenance report from the following equipment readings.

Suggest what additional data would help improve failure prediction.

9. Evaluation Criteria

| Area | Weight | Excellent Criteria |
| --- | --- | --- |
| Predictive Maintenance Foundations and Prompt Engineering | 10% | Understands maintenance use case, sensor data, failure scenarios, and practical maintenance prompts |
| Python Fundamentals | 10% | Can explain and run basic Python code in Google Colab |
| Data Analytics | 15% | Reads, cleans, explores, and summarizes the dataset |
| Visualization and Power BI Dashboard | 15% | Creates useful Colab charts and a clear Power BI dashboard |
| Machine Learning Model | 20% | Builds a functional failure prediction model and explains key metrics |
| Evaluation and Optimization | 15% | Analyzes errors, compares model versions, improves features/settings, and explains optimization decisions |
| Final Demo and Presentation | 15% | Presents a clear Colab demo, Power BI dashboard, recommendation logic, and learning summary |

10. Final Demo Requirements

The demo should run inside Google Colab as the default technical demo.

The user should be able to change equipment readings such as temperature, vibration, torque, pressure, and tool wear.

The model should return a failure prediction or failure probability.

The output should include risk level and a simple maintenance recommendation.

The Power BI dashboard should summarize key historical insights from the dataset.

The final presentation should include problem statement, dataset overview, Power BI screenshots, ML model results, optimization results, demo screenshots, challenges, and learning outcomes.

11. Public Dataset Reference

The attached training file is synthetic and intended for educational use. Students may optionally review the AI4I 2020 Predictive Maintenance Dataset from UCI as a public reference for a similar industrial predictive maintenance dataset.

Reference link: https://archive.ics.uci.edu/ml/datasets/AI4I+2020+Predictive+Maintenance+Dataset